## Tabelle1
Status | Priority | Task | Developer | Due | Notes | ID
☒ | low | think about how to integrate PSO and Newton into GUI | Devansh | 2021-03-19 |  | 1
☒ | medium | write tasklist and auxilliary management documents | Tristan | 2021-03-18 |  | 2
☒ | high | show Devansh how to use WinForms | Tristan | 2021-03-19 |  | 3
| low | add SIR model to "Epidemics Plugin" document |  |  |  | 4
☒ | medium | fix PDE formulation in seird_pde.h |  |  | PDE model not working yet | 5
☒ | medium | Investigate feasibility of GTK based UI for Linux and MacOS | Tristan | 2021-03-20 | GTK might be suitable for cross plattform development | 6
☒ | high | Add possibility to load and display experimental Data in SEIRD model of GUI | Tristan | 2021-03-20 |  | 7
☒ | high | Integrate Parameter Estimator into GUI | Devansh | 2021-03-24 | Parameter Estimator must be integrated into the GUI before the next meeting with Arne and Babett | 8
☒ | low | Create GTK Prototype |  |  |  | 9
☐ | low | Investigate if Mono compiles the Windows Forms GUI |  |  |  | 10
☒ | high | Plotting function for PSO | Tristan | 2021-03-24 |  | 11
☒ | high | Plotting experimental data in Form4 | Devansh | 2021-03-24 |  | 12
☒ | medium | Cancel button for folder-chooser in both tabs. | Yannick | 23/05/2021 | Pressing cancel crashes the program | 13
☒ | high | ConstrainedOptimization Buttons | Tristan | 2021-03-12 | Connect Run PSO and GaussNewton in the PDE form | 14
☒ | low | Plot experimental data in SEIRD ODE | Tristan | 2021-03-21 |  | 15
☒ | medium | Labels for the graphs in the SEIRD ODE |  |  |  | 16
☐ | low | Fix button margins in SERID PDE form |  |  |  | 17
☐ | medium | Integrate Marvins‘ Model into GUI |  |  |  | 18
☐ | medium | Integrate Devanshs‘ Model into GUI |  |  |  | 19
☐ | medium | Fix scale of experimental data plot in SEIRD ODE Widget |  |  | Currently experimental data is not plotted with respect to the scale of the sim plots | 20
☒ | medium | Enlarge Heatmaps in SEIRD PDE Widget | Yannick | 24/03/2021 | Enlarge SEIRD PDE heatmaps by clicking on them or other means | 21
☐ | medium | Create proper Jacobian in seird_pde.h | Marvin |  | Jacobi Matrix has to be created for the PDE problem. | 22
☐ | low | Change colors of the labels according to the color of the graph in the plot in SEIRD Widget |  |  | This task might not even be a good idea, as different label colors might not be seen easily on the background | 23
☐ | high | Fix wrong diffusion results in SEIRD PDE |  |  | When diffusion is turned on, the model gives implausible values (negatives and NaNs). This might be due to numerical instability. Therefore, this problem might be solved if the task with ID 22 is finished. It should also he investigated, of the diffusion works with a very small stepsize (below 10e-7). | 24
☐ | low | Add save to file possibility in the SEIRD Widget |  |  | Just like in the PDE Version, the user might want to either save the plot of the output of a simulation to file. | 25
☐ | low | Run sim on server |  |  | For the PDE version, it would be cool if there was the possibility to run the sim on a server (through ssh commands for example) and display the results all from the gui. | 26
☐ | low | Add progress bar |  |  | For long running sims or the optimization, it would be nice to have something like a progress bar oe the like | 27
☐ | medium | Add more diagnostics from the optimizations runs |  |  | During an optimization procedure, a lot of information is relayed to the user (see summary_of_estimation.txt). Ideally, this information would be shown during the optimization to the user (just like in the command line) | 28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55

## Tabelle2
Developers | Priority | Status
Devansh | high | ☒
Yannick | medium | ☐
Tristan | low
Marvin
Jonas