## Tabelle1
Status | Priority | Task | Developer | Due | Notes | ID
☒ | low | think about how to integrate PSO and Newton into GUI | Devansh | 2021-03-19 |  | 1
☒ | medium | write tasklist and auxilliary management documents | Tristan | 2021-03-18 |  | 2
☒ | high | show Devansh how to use WinForms | Tristan | 2021-03-19 |  | 3
☐ | low | add SIR model to "Epidemics Plugin" document |  |  |  | 4
☐ | medium | fix PDE formulation in seird_pde.h |  |  | PDE model not working yet | 5
☒ | medium | Investigate feasibility of GTK based UI for Linux and MacOS | Tristan | 2021-03-20 | GTK might be suitable for cross plattform development | 6
☒ | high | Add possibility to load and display experimental Data in SEIRD model of GUI | Tristan | 2021-03-20 |  | 7
☒ | high | Integrate Parameter Estimator into GUI | Devansh | 2021-03-24 | Parameter Estimator must be integrated into the GUI before the next meeting with Arne and Babett | 8
☒ | low | Create GTK Prototype |  |  |  | 9
☐ | low | Investigate if Mono compiles the Windows Forms GUI |  |  |  | 10
☒ | high | Plotting function for PSO |  | 2021-03-24 |  | 11
☒ | high | Plotting experimental data in Form4 |  | 2021-03-24 |  | 12

## Tabelle2
Developers | Priority | Status
Devansh | high | ☒
Yannick | medium | ☐
Tristan | low
Jonas